# Jira Stories — Finestra ISO 20022 (pain.001.001.09) Wire Migration

Parent Epic suggestion: WEBLOC-XXXX: Migrate Wire Transfer File Generation from PayPlus/Fedwire XML to ISO 20022 pain.001.001.09 (Finestra)

## Story 1 — Field Mapping & Sign-Off Documentation

Type: Task

Summary: Produce and circulate ISO 20022 field mapping document for Finestra sign-off

Description:

Create a mapping document covering all PayPlus/Fedwire fields currently used in wire generation, mapped to their ISO 20022 pain.001.001.09 equivalents. Include an "Open Items" section for fields without a confirmed mapping. Send to Finestra for written sign-off or corrections.

Acceptance Criteria:

- Mapping doc covers all fields in current pain001 (002).xml sample

- Open items table identifies all ambiguous/unmapped fields with proposed defaults

- Document sent to Finestra; response tracked

- Sign-off (or documented corrections) received before Story 3 begins

Story Points: 2

Blocks: Story 3, Story 4

## Story 2 — Define Mapping Table Schema in SQL Server

Type: Task

Summary: Create ISOWireFieldMapping table and seed static/known values

Description:

Create a SQL Server table to hold field-to-ISO-element mappings, including static values (USABA, CTR, TRF, CACC, USD, BusChanl code) and dynamic field references. This drives the generation stored procedure and allows non-dev updates to mappings.

Acceptance Criteria:

- ISOWireFieldMapping table created with columns for source field, ISO path, static flag/value, active flag, notes

- Static values seeded (clearing system code, payment method, account type code, currency, local instrument code, business channel)

- Table reviewed against signed-off mapping doc from Story 1

Story Points: 2

Depends on: Story 1 (for confirmed static values)

## Story 3 — Data Access Layer: Wire Data DTO + Retrieval Stored Procedure

Type: Story

Summary: Build up_GetWireDataForISOExport SP and corresponding C# DTO(s)

Description:

Instead of generating XML in SQL, build a stored procedure that returns a flat result set with all fields needed for ISO 20022 generation (originator, beneficiary, banks, intermediary, amounts, references, Finestra-specific fields). Define matching C# DTO class(es) (e.g. WireExportDto) that all downstream classes will consume. This is the foundation everyone else builds on — do this first and get it stable quickly.

Acceptance Criteria:

- SP returns one row per wire with all fields identified in the mapping doc (Section 1), nulls allowed for optional/conditional fields

- DTO explicitly includes ThirdPartyBankABANumber (nullable), ThirdPartyBankAccountNumber (nullable), ThirdPartyBankName (nullable), ThirdPartyBankAddressLine1-3 (nullable) to support {4100} conditional logic

- DTO includes all 3 Originator address lines (OFAC requires minimum 2 populated)

- DTO reviewed/agreed by all developers assigned to Stories 4a/4b/5 before they start (shared contract)

- Unit test confirms SP returns expected data for: (a) standard wire, (b) third party wire with ABA, (c) third party wire with account number

Story Points: 3

Depends on: Story 2

Blocks: Stories 4a, 4b, 5

## Story 4a — C# Model Classes: GroupHeader & PaymentInformation (Debtor side)

Type: Story

Summary: Build GroupHeader and PaymentInformation (Dbtr/DbtrAgt/DbtrAcct) classes with XML serialization attributes

Description:

Create C# classes representing GrpHdr (MsgId, CreDtTm, NbOfTxs, CtrlSum, InitgPty) and the PmtInf header through the debtor side (Dbtr, DbtrAcct, DbtrAgt, PmtTpInf/LclInstrm, ReqdExctnDt), decorated with [XmlElement]/[XmlAttribute] (or built via System.Xml.Linq XElement, per team preference) targeting the pain.001.001.09 namespace.

Acceptance Criteria:

- Classes for GroupHeader, PaymentInformationHeader, Debtor, DebtorAccount, DebtorAgent created

- Address parsing logic (legacy single-line → StrtNm/BldgNb/TwnNm/CtrySubDvsn/PstCd) implemented and unit tested; best-effort parse with fallback to full text in StrtNm

- `Ctry='US'` hardcoded on Dbtr/PstlAdr/Ctry and DbtrAgt/FinInstnId/PstlAdr/Ctry — this field did not exist in legacy Fedwire format; required by pain.001 PstlAdr

- OFAC: Enforce minimum 2 populated address lines on Dbtr/PstlAdr; log warning if incomplete

- Classes populate correctly from WireExportDto (Story 3)

- Serialized output for this section validated against pain.001.001.09 schema fragment

Story Points: 5

Depends on: Story 3 (DTO contract)

Can run in parallel with: 4b, 5

## Story 4b — C# Model Classes: CreditTransferTransaction (Creditor/Beneficiary side)

Type: Story

Summary: Build CreditTransferTransactionInformation classes (Amt, IntrmyAgt1, CdtrAgt, Cdtr, CdtrAcct, Purp, RmtInf)

Description:

Create C# classes for the CdtTrfTxInf block: amount/currency (Amt/InstdAmt with Ccy attribute), conditional intermediary bank (IntrmyAgt1/IntrmyAgt1Acct), creditor agent (beneficiary bank), creditor (beneficiary) with parsed address, creditor account, purpose, and remittance info.

Acceptance Criteria:

- Classes for CreditTransferTransactionInformation, Amount, IntermediaryAgent, CreditorAgent, Creditor, CreditorAccount, Purpose, RemittanceInformation created

- InstdAmt serializes with correct Ccy="USD" attribute; amount calculated by dividing raw integer by 100 (2 implied decimals — e.g. 000001234567 = 12345.67)

- Third party wire scaffolding (IDCode=F): When ThirdPartyBankABANumber present, emit IntrmyAgt1/FinInstnId/ClrSysMmbId/MmbId with USABA + third party ABA, and IntrmyAgt1/FinInstnId/Nm with bank name. Build behind feature flag pending Finestra confirm.

- Third party wire scaffolding (IDCode=D): When ThirdPartyBankAccountNumber present (no ABA), emit IntrmyAgt1/FinInstnId/Nm with bank name + IntrmyAgt1Acct/Id/Othr/Id with account number. Build behind feature flag pending Finestra confirm.

- When neither third party field present, omit IntrmyAgt1/IntrmyAgt1Acct entirely

- `Ctry='US'` hardcoded on Cdtr/PstlAdr/Ctry and CdtrAgt/FinInstnId/PstlAdr/Ctry — this field did not exist in legacy Fedwire format; required by pain.001 PstlAdr

- Address parsing for beneficiary (StrtNm, BldgNb, TwnNm, CtrySubDvsn, PstCd) implemented and unit tested; best-effort parse with fallback to full text in StrtNm

- OFAC: Dbtr/PstlAdr minimum 2 address lines enforced with validation warning if incomplete

- Serialized output validated for: standard wire, third party ABA wire, third party account wire

Story Points: 5

Depends on: Story 3 (DTO contract)

Can run in parallel with: 4a, 5

## Story 4c — Third Party Wire Handling (IDCode F and D)

Type: Story

Summary: Implement conditional third party bank logic for {4100} scenarios once Finestra confirms pain.001 structure

Description:

Legacy {4100} BeneficiaryFI tag identifies a third party bank when the beneficiary's bank differs from the receiving institution. Two scenarios exist: IDCode=F (third party identified by ABA routing number) and IDCode=D (third party identified by account number). pain.001 handles these differently — Finestra must confirm which elements to use before this story can be fully implemented. Code scaffolding and feature flag can be built in Story 4b; this story completes and hardens the implementation once sign-off is received.

Acceptance Criteria:

- Finestra sign-off received confirming IntrmyAgt1 assumption for IDCode=F and IDCode=D (Open Items Q1 and Q2)

- If confirmed: feature flag removed, IntrmyAgt1 (IDCode=F) and IntrmyAgt1Acct (IDCode=D) implementations hardened

- If Finestra provides a different structure: implementation updated accordingly from scaffolding built in Story 4b

- Ctry='US' confirmed on IntrmyAgt1/FinInstnId/PstlAdr/Ctry per global address assumption

- Unit tests cover all three wire scenarios end-to-end: standard, third party ABA, third party account

- OFAC address validation confirmed passing for all scenarios

Story Points: 3

Depends on: Story 4b (scaffolding), Story 1 Open Items Q1/Q2 (Finestra sign-off)

Can run in parallel with: Story 5 once scaffolding from 4b is in place

Type: Story

Summary: Build SupplementaryData/Envelope classes for Finestra-specific block (supl.001.001.01)

Description:

Create C# classes representing the nested SplmtryData/Envlp/Document supplementary data blocks containing TxTrcId, InstrTrcId, InstrRcptId, BusChanl, and the Ext block (debitAccountType, internationalPayment, instMethod, waiveFees). These nested Document elements use a different namespace (supl.001.001.01) than the outer document — handle this explicitly (e.g. separate XmlSerializerNamespaces or XNamespace per element).

Acceptance Criteria:

- Classes for SupplementaryData, Envelope, SupplementaryDocument, ExtensionData created

- Nested Document elements correctly serialize with supl.001.001.01 namespace, distinct from outer pain.001.001.09

- All Ext fields populated per confirmed/default values from Story 1 mapping doc

- Output validated against Finestra sample/test file structure

Story Points: 3

Depends on: Story 3 (DTO contract), Story 1 (Open Items confirmation)

Can run in parallel with: 4a, 4b

## Story 6 — Integration: Assemble, Serialize, and Output Final ISO 20022 Document

Type: Story

Summary: Compose all model classes into root Document, serialize with correct namespaces, and produce output file

Description:

Build the top-level Document/CstmrCdtTrfInitn class that composes the components from Stories 4a, 4b, and 5 into the final structure. Implement serialization (handling the dual-namespace requirement between outer pain.001.001.09 and inner supl.001.001.01 blocks), validate well-formedness/schema, and write the output file to the location expected by SSIS/Finestra intake.

Acceptance Criteria:

- Root Document/CstmrCdtTrfInitn class composes GroupHeader, PaymentInformation (incl. nested 4a/4b components), and SupplementaryData

- Final serialized XML carries correct namespace declarations at both outer and inner Document levels

- Full output validates against pain.001.001.09 schema with zero errors, for wires both with and without intermediary

- Output file written in format/location consumable by existing SSIS package (or new lightweight job — coordinate with Story 7)

Story Points: 3

Depends on: Stories 4a, 4b, 5

## Story 7 — SSIS Integration / File Output

Type: Task

Summary: Update SSIS package to trigger ISO 20022 generation and consume output file

Description:

Update the existing SSIS package/job that currently calls the PayPlus XML generation SP to instead trigger the new C# generation process (Story 6) and pick up its output file for delivery to Finestra's intake location/naming convention.

Acceptance Criteria:

- SSIS package (or replacement job) triggers C# generation and writes/picks up output file

- File naming convention confirmed with Finestra (per Story 1 open item on delivery mechanism)

- End-to-end test file generated and validated

Story Points: 3

Depends on: Story 6, Story 1 (delivery mechanism confirmation)

## Story 8 — Parallel Run / Validation Testing

Type: Task

Summary: Run new ISO 20022 generation in parallel with legacy PayPlus format for validation

Description:

For a defined test period, generate both legacy PayPlus XML and new ISO 20022 XML for the same wires, compare field-by-field, and validate ISO output against schema and any Finestra test/UAT environment.

Acceptance Criteria:

- Parallel output generated for a sample set of wires (incl. wires with/without intermediary banks)

- Field-by-field comparison documented

- Finestra UAT acceptance (if available) or schema validation passes with zero errors

- Sign-off from business stakeholders to cut over

Story Points: 3

Depends on: Story 7

## Story 9 (Stretch/Follow-up) — pain.002 Acknowledgment Handling

Type: Story (candidate for future sprint)

Summary: Ingest and process Finestra acknowledgment/status report, if required

Description:

Per Open Item in Story 1, if Finestra returns a pain.002 Customer Payment Status Report, build handling to ingest and reconcile against submitted wires.

Acceptance Criteria:

- TBD pending Finestra confirmation

- Out of scope for initial November cutover unless required

Story Points: TBD (placeholder)

Depends on: Story 1 confirmation

# Suggested Sprint Grouping

- Sprint 1: Stories 1, 2, 3 (mapping doc v2 out the door, mapping table, DTO/SP foundation — Story 3 unblocks parallel work. Third party fields in DTO from day 1.)

- Sprint 2: Stories 4a, 4b, 5 — 3 developers in parallel. 4b includes third party scaffolding behind feature flag.

- Sprint 3: Story 4c (third party hardening — depends on Finestra Q1/Q2 sign-off), Story 6 (integration), Story 7 (SSIS)

- Sprint 4: Story 8 (parallel run/validation — must include third party wire test cases)

- Backlog: Story 9

# Risk Notes for Grooming

Third party wire risk (NEW): Stories 4b/4c depend on Finestra confirming how {4100} IDCode=F and IDCode=D map to pain.001 elements. This is the highest-priority open item in the mapping doc. Scaffolding can be built in 4b behind a feature flag, but hardening (4c) is blocked until sign-off. Recommend escalating Q1/Q2 from the mapping doc to Finestra immediately.

Amount decimal correction: Original mapping assumed 3 implied decimals. Confirmed from Webloc Wire Tag spec as 2 implied decimals. SP in Story 3 and Amount class in Story 4b must divide raw integer by 100, not 1000.

OFAC compliance: Originator address minimum 2 lines is a compliance requirement, not just a data quality issue. Story 4b must enforce this with a validation warning or hard error.

Finestra sign-off dependency: Stories 4c and 5 both depend on Finestra open items being resolved. If sign-off is delayed, recommend proceeding with documented proposed defaults under feature flags and flagging as technical debt — November deadline does not allow waiting indefinitely.